## Detail Steps
Week # | Date Range | Task | Completed? (Y/N) | Notes/Blockers
Week 1 | 2025-05-13 to 2025-05-19 | Finalize roadmap and confirm API inputs/outputs
Week 1 | 2025-05-13 to 2025-05-19 | Define HTML page layout for calculator & static pages
Week 1 | 2025-05-13 to 2025-05-19 | Modularize quote logic (split GP vs LCP flows)
Week 1 | 2025-05-13 to 2025-05-19 | Build HTML static version of calculator & navigation
Week 1 | 2025-05-13 to 2025-05-19 | Connect data entry to backend calculation via fetch
Week 1 | 2025-05-13 to 2025-05-19 | Validate calculation logic with test entries
Week 1 | 2025-05-13 to 2025-05-19 | Add mobile responsiveness & error handling
Week 1 | 2025-05-13 to 2025-05-19 | Move frontend to React, backend to hosted MongoDB
Week 1 | 2025-05-13 to 2025-05-19 | Prepare team onboarding doc & investor demo sheet
Week 1 | 2025-05-13 to 2025-05-19 | UAT testing & launch MVP
Week 2 | 2025-05-20 to 2025-05-26 | Finalize roadmap and confirm API inputs/outputs
Week 2 | 2025-05-20 to 2025-05-26 | Define HTML page layout for calculator & static pages
Week 2 | 2025-05-20 to 2025-05-26 | Modularize quote logic (split GP vs LCP flows)
Week 2 | 2025-05-20 to 2025-05-26 | Build HTML static version of calculator & navigation
Week 2 | 2025-05-20 to 2025-05-26 | Connect data entry to backend calculation via fetch
Week 2 | 2025-05-20 to 2025-05-26 | Validate calculation logic with test entries
Week 2 | 2025-05-20 to 2025-05-26 | Add mobile responsiveness & error handling
Week 2 | 2025-05-20 to 2025-05-26 | Move frontend to React, backend to hosted MongoDB
Week 2 | 2025-05-20 to 2025-05-26 | Prepare team onboarding doc & investor demo sheet
Week 2 | 2025-05-20 to 2025-05-26 | UAT testing & launch MVP
Week 3 | 2025-05-27 to 2025-06-02 | Finalize roadmap and confirm API inputs/outputs
Week 3 | 2025-05-27 to 2025-06-02 | Define HTML page layout for calculator & static pages
Week 3 | 2025-05-27 to 2025-06-02 | Modularize quote logic (split GP vs LCP flows)
Week 3 | 2025-05-27 to 2025-06-02 | Build HTML static version of calculator & navigation
Week 3 | 2025-05-27 to 2025-06-02 | Connect data entry to backend calculation via fetch
Week 3 | 2025-05-27 to 2025-06-02 | Validate calculation logic with test entries
Week 3 | 2025-05-27 to 2025-06-02 | Add mobile responsiveness & error handling
Week 3 | 2025-05-27 to 2025-06-02 | Move frontend to React, backend to hosted MongoDB
Week 3 | 2025-05-27 to 2025-06-02 | Prepare team onboarding doc & investor demo sheet
Week 3 | 2025-05-27 to 2025-06-02 | UAT testing & launch MVP
Week 4 | 2025-06-03 to 2025-06-09 | Finalize roadmap and confirm API inputs/outputs
Week 4 | 2025-06-03 to 2025-06-09 | Define HTML page layout for calculator & static pages
Week 4 | 2025-06-03 to 2025-06-09 | Modularize quote logic (split GP vs LCP flows)
Week 4 | 2025-06-03 to 2025-06-09 | Build HTML static version of calculator & navigation
Week 4 | 2025-06-03 to 2025-06-09 | Connect data entry to backend calculation via fetch
Week 4 | 2025-06-03 to 2025-06-09 | Validate calculation logic with test entries
Week 4 | 2025-06-03 to 2025-06-09 | Add mobile responsiveness & error handling
Week 4 | 2025-06-03 to 2025-06-09 | Move frontend to React, backend to hosted MongoDB
Week 4 | 2025-06-03 to 2025-06-09 | Prepare team onboarding doc & investor demo sheet
Week 4 | 2025-06-03 to 2025-06-09 | UAT testing & launch MVP
Week 5 | 2025-06-10 to 2025-06-16 | Finalize roadmap and confirm API inputs/outputs
Week 5 | 2025-06-10 to 2025-06-16 | Define HTML page layout for calculator & static pages
Week 5 | 2025-06-10 to 2025-06-16 | Modularize quote logic (split GP vs LCP flows)
Week 5 | 2025-06-10 to 2025-06-16 | Build HTML static version of calculator & navigation
Week 5 | 2025-06-10 to 2025-06-16 | Connect data entry to backend calculation via fetch
Week 5 | 2025-06-10 to 2025-06-16 | Validate calculation logic with test entries
Week 5 | 2025-06-10 to 2025-06-16 | Add mobile responsiveness & error handling
Week 5 | 2025-06-10 to 2025-06-16 | Move frontend to React, backend to hosted MongoDB
Week 5 | 2025-06-10 to 2025-06-16 | Prepare team onboarding doc & investor demo sheet
Week 5 | 2025-06-10 to 2025-06-16 | UAT testing & launch MVP
Week 6 | 2025-06-17 to 2025-06-23 | Finalize roadmap and confirm API inputs/outputs
Week 6 | 2025-06-17 to 2025-06-23 | Define HTML page layout for calculator & static pages
Week 6 | 2025-06-17 to 2025-06-23 | Modularize quote logic (split GP vs LCP flows)
Week 6 | 2025-06-17 to 2025-06-23 | Build HTML static version of calculator & navigation
Week 6 | 2025-06-17 to 2025-06-23 | Connect data entry to backend calculation via fetch
Week 6 | 2025-06-17 to 2025-06-23 | Validate calculation logic with test entries
Week 6 | 2025-06-17 to 2025-06-23 | Add mobile responsiveness & error handling
Week 6 | 2025-06-17 to 2025-06-23 | Move frontend to React, backend to hosted MongoDB
Week 6 | 2025-06-17 to 2025-06-23 | Prepare team onboarding doc & investor demo sheet
Week 6 | 2025-06-17 to 2025-06-23 | UAT testing & launch MVP
Week 7 | 2025-06-24 to 2025-06-30 | Finalize roadmap and confirm API inputs/outputs
Week 7 | 2025-06-24 to 2025-06-30 | Define HTML page layout for calculator & static pages
Week 7 | 2025-06-24 to 2025-06-30 | Modularize quote logic (split GP vs LCP flows)
Week 7 | 2025-06-24 to 2025-06-30 | Build HTML static version of calculator & navigation
Week 7 | 2025-06-24 to 2025-06-30 | Connect data entry to backend calculation via fetch
Week 7 | 2025-06-24 to 2025-06-30 | Validate calculation logic with test entries
Week 7 | 2025-06-24 to 2025-06-30 | Add mobile responsiveness & error handling
Week 7 | 2025-06-24 to 2025-06-30 | Move frontend to React, backend to hosted MongoDB
Week 7 | 2025-06-24 to 2025-06-30 | Prepare team onboarding doc & investor demo sheet
Week 7 | 2025-06-24 to 2025-06-30 | UAT testing & launch MVP
Week 8 | 2025-07-01 to 2025-07-07 | Finalize roadmap and confirm API inputs/outputs
Week 8 | 2025-07-01 to 2025-07-07 | Define HTML page layout for calculator & static pages
Week 8 | 2025-07-01 to 2025-07-07 | Modularize quote logic (split GP vs LCP flows)
Week 8 | 2025-07-01 to 2025-07-07 | Build HTML static version of calculator & navigation
Week 8 | 2025-07-01 to 2025-07-07 | Connect data entry to backend calculation via fetch
Week 8 | 2025-07-01 to 2025-07-07 | Validate calculation logic with test entries
Week 8 | 2025-07-01 to 2025-07-07 | Add mobile responsiveness & error handling
Week 8 | 2025-07-01 to 2025-07-07 | Move frontend to React, backend to hosted MongoDB
Week 8 | 2025-07-01 to 2025-07-07 | Prepare team onboarding doc & investor demo sheet
Week 8 | 2025-07-01 to 2025-07-07 | UAT testing & launch MVP

## Overview
Week # | Dates | Task Category | Goal/Deliverable | Completed? | Notes/Blockers
1 | May 11–17 | Planning | Finalize roadmap, confirm all API inputs/outputs
|  | Frontend Architecture | Define HTML page layout for calculator & static pages
|  | Backend Refactor | Modularize quote logic (split GP vs LCP flows
2 | May 18–24 | UI Implementation | Build HTML static version of calculator & navigation
|  | API Middleware | Connect basic data entry → backend calculation via fetch
3 | May 25–31 | Testing | Validate calculation logic with test entries
|  | UI Polish | Move frontend to React, backend to hosted MongoDB
4 | June 1–7 | Deployment Prep | Move frontend to React, backend to hosted MongoDB
|  | Documentation | Prepare team onboarding doc &
5 | June 8–14 | QA + Go-Live | UAT testing & launch MVP